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Overview
Project background and description 
	
	This project is for capacity relief / capacity management of Comcast equipment. We are looking to upgrade the equipment to better serve existing customers and ensure current customers can expect reliability and stability for their Comcast services.



Project scope 
	
	The scope of the project in include boring and placing 2 – 2inch conduit beginning from behind 522 Kryptonite Dr, Castle Rock, 80108 to the intersection of Sapphire Pointe Blvd and Baguette Dr where current equipment exists following the right of way and staying in soft surface wherever possible. A new Pedestal and Vault (Housing storage of fiber) will be placed behind 522 Kryptonite Dr, Castle Rock, 80108 following Cinnabar Dr south until the intersection on Sapphire Point Blvd, there a new vault will also be placed and bore will continue east past Iridium way where another vault will be placed due to distance and future development. As the bore continues east another vault will be placed directly after the round about due to same reasons listed previously. One last vault will be placed shortly after we cross Kryptonite Dr due to distance between vault and we will tie into our existing equipment at the intersection of Baguette Dr and Sapphire Pointe Blvd. New 48ct fiber will be pulled along this route to connect new equipment to the existing plant.



Safety
	
	We have multiple safety measures in place to guarantee safety of residents and crew that will be onsite. We have traffic control plans ready to deploy once work has begun. We will have multiple flaggers at the start and end of the project including any road crossing to direct traffic safely. Several signs will be present on site to inform drivers of ongoing work.



Expectations
	
	We believe we can execute this job in roughly 10 business days for the bore portion of the job. We will also revisit the job directly after completion to get any restoration estimated and completed in a timely manner, traffic control will also be present during restoration to ensure safety of our crews and residents. This project will bring relief and stability to current residents in terms of service to the home and will help new Comcast customers receive the new and improved services.




1
